## sheet1
Food_Prices_Across_Bangladesh
name | status | startDate | dueDate | 8/22 | 8/23 | 8/24 | 8/25 | 8/26 | 8/27 | 8/28 | 8/29 | 8/30 | 8/31 | 9/1 | 9/2 | 9/3 | 9/4 | 9/5 | 9/6 | 9/7 | 9/8 | 9/9 | 9/10 | 9/11 | 9/12 | 9/13 | 9/14 | 9/15 | 9/16 | 9/17 | 9/18 | 9/19 | 9/20 | 9/21 | 9/22 | 9/23 | 9/24 | 9/25 | 9/26 | 9/27 | 9/28 | 9/29 | 9/30 | 10/1 | 10/2 | 10/3 | 10/4 | 10/5 | 10/6 | 10/7 | 10/8 | 10/9 | 10/10 | 10/11 | 10/12 | 10/13 | 10/14 | 10/15 | 10/16 | 10/17 | 10/18 | 10/19 | 10/20 | 10/21 | 10/22 | 10/23 | 10/24 | 10/25 | 10/26 | 10/27 | 10/28 | 10/29 | 10/30 | 10/31 | 11/1 | 11/2 | 11/3 | 11/4 | 11/5 | 11/6 | 11/7 | 11/8 | 11/9 | 11/10 | 11/11 | 11/12 | 11/13 | 11/14 | 11/15 | 11/16 | 11/17 | 11/18 | 11/19 | 11/20 | 11/21 | 11/22 | 11/23 | 11/24 | 11/25 | 11/26 | 11/27 | 11/28 | 11/29 | 11/30 | 12/1 | 12/2 | 12/3 | 12/4 | 12/5 | 12/6 | 12/7 | 12/8 | 12/9 | 12/10 | 12/11 | 12/12
Complete project execution | Doing | 8/22 | 12/12
Requirements | Done | 8/22 | 9/5
Analysis | Done | 9/7 | 9/19
Modiling | Doing | 9/19 | 11/28
Er_Diagram | Done | 9/19 | 9/26
DFD | Done | 9/27 | 10/17
Use Case | Done | 10/18 | 10/31
Class Diagram | Done | 10/31 | 11/7
Activity & sequence | Done | 11/8 | 11/21
Gantt Chart & Budget | Doing | 11/21 | 11/28
Implement | Doing | 9/7 | 12/4
User Login | Done | 9/21 | 10/3
Admin Login | Done | 10/5 | 10/17
top-header & header | Done | 10/12 | 10/24
Website Front page | Done | 10/26 | 10/31
Config, footer & side-menu | Done | 10/19 | 10/24
User portal | Doing | 10/5 | 12/5
Admin portal | Doing | 10/12 | 12/5
My_SQL | Doing | 11/9 | 12/5
Testing | ToDo | 12/5 | 12/12